## General
Team Number: | Team 3
Week: | 6

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Email signup and authentication service
2 | Email login and authentication service
3 | Create signup screen
4 | Create login screen
5 | Create main menu screen
6 | Create matchmaking service
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Google Sign-In implementation for Unity
2
3
4
5
C. | List your accomplishments from the previous week
1 | Created trello board to keep track of tasks and responsibilities
2 | Fleshed out user stories into concrete tasks to be done
3 | Created initial Unity project and added to version control
4 | Created Firebase account
5
6
7
8