## General
Team Number: | Team 3
Week: | 9

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Investigate Google SSO
2 | Add Android Libraries to support Google SSO
3 | Enable Firebase Authentication to support Google SSO
4
5
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1
2
3
4
5
C. | List your accomplishments from the previous week
1 | Email signup and authentication service
2 | Email login and authenticatino service
3 | Created signup screen
4 | Created login screen
5 | Created main menu screen
6
7
8